## 核查单
核查单 | 状态 | 时间 | 备注
读第1章
读第2章
读第3章
读第4章
读第5章
读第6章
读第7章
读第8章 |  | 20211106
读第9章 |  | 20211114
读第10章 |  | 20211208
读第11章 |  | 20211225
整理笔记第1章 |  | 20211106
整理笔记第2章 |  | 20211106
整理笔记第3章 |  | 20211108
整理笔记第4章 |  | 20211108
整理笔记第5章 |  | 20211108
整理笔记第6章 |  | 20211109
整理笔记第7章 |  | 20211109
整理笔记第8章 |  | 20211109
整理笔记第9章 |  | 20211114
整理笔记第10章 |  | 20211208
整理笔记第11章 |  | 20211225
整理各章节的Core Concept |  |  | 梳理Core Concept矩阵
整理流程图 |  |  | 用自己的理解概述各流程
视频0章 |  | 20211225 | 开篇
视频第1章
视频第2章
视频第3章
视频第4章
视频第5章
视频第6章
视频第7章
视频第8章
复习第1章
复习第2章
复习第3章
复习第4章
复习第5章
复习第6章
复习第7章
复习第8章
复习第9章
复习第10章
复习第11章

## 概要
Core Concept | During Business Analysis Planning and Monitoring, business analysts...
Change: the act of transformation in response to a need.
Need: a problem or opportunity to be addressed.
Solution: a specific way of satisfying one or more needs in a context.
Stakeholder: a group or individual with a relationship to the change, the need, or the solution.
Value: the worth, importance, or usefulness of something to a stakeholder within a context.
Context: the circumstances that influence, are influenced by, and provide understanding of the change.

## chapter1
章节 | 标题 | 概要 | 理解
1 | Introduction
2 | Business Analysis Key Concepts | define the key terms needed to understand all other content, concepts, and ideas within the BABOK Guide
3 | Business Analysis Planning and Monitoring | describe the tasks that business analysts perform to organize and coordinate the efforts of business analysts and stakeholders. These tasks produce outputs that are used as key inputs and guidelines for the other tasks throughout the BABOK® Guide.
4 | Elication and Collaboration | describes the tasks that business analysts perform to prepare for and conduct elicitation activities and confirm the results obtained. It also describes the communication with stakeholders once the business analysis information is assembled and the ongoing collaboration with them throughout the business analysis activities.
5 | Requirements Life Cycle Management | describes the tasks that business analysts perform in order to manage and maintain requirements and design information from inception to retirement. These tasks describe establishing meaningful relationships between related requirements and designs, and assessing, analyzing and gaining consensus on proposed changes to requirements and designs.
6 | Strategy Analysis | describes the business analysis work that must be performed to collaborate with stakeholders in order to identify a need of strategic or tactical importance (the business need), enable the enterprise to address that need, and align the resulting strategy for the change with higher- and lower-level strategies.
7 | Requirements Analysis and Design Definition | describes the tasks that business analysts perform to structure and organize requirements discovered during elicitation activities, specify and model requirements and designs, validate and verify information, identify solution options that meet business needs, and estimate the potential value that could be realized for each solution option. This knowledge area covers the incremental and iterative activities ranging from the initial concept and exploration of the need through the transformation of those needs into a particular recommended solution.
8 | Solution Evaluation | describes the tasks that business analysts perform to assess the performance of and value delivered by a solution in use by the enterprise, and to recommend removal of barriers or constraints that prevent the full realization of the value. | 1. Prototypes or Proofs of Concept 2. Pilot or Beta releases 3. Operational releases
9 | Underlying Competencies | provide a description of the behavirours, characteristics, knowledge, and personal qualtites that support the effective practice of business analysis
10 | Techniques | provide a means to perform business analysis tasks. the techniques described in the BABOK Guide are intended to cover the most common and widespread techniques practiced within the business analysis community
11 | Perspectives | describe various views of business analysis. Perspectives help business analysts working from various points of view to better perform business analysis, given the context of the initiative. | • Agile, • Business Intelligence, • Information Technology, • Business Architecture, and • Business Process Management

## chapter2
章节 | 标题 | 概念 |  | 理解
2.1 | The Business Analysis Core Concept Model | Change | The act of transformation in response to a need. Change works to improve the performance of an enterprise. These improvements are deliberate and controlled through business analysis activities. | 根据需要而转变的行为
|  | Need | A problem or opportunity to be addressed. Needs can cause changes by motivating stakeholders to act. Changes can also cause needs by eroding or enhancing the value delivered by existing solutions. | 需要解决的问题或机会
|  | Solution | A specific way of satisfying one or more needs in a context. A solution satisfies a need by resolving a problem faced by stakeholders or enabling stakeholders to take advantage of an opportunity.
|  | Stakeholder | A group or individual with a relationship to the change, the need, or the solution. Stakeholders are often defined in terms of interest in, impact on, and influence over the change. Stakeholders are grouped based on their relationship to the needs, changes, and solutions. | 干系人
|  | Value | The worth, importance, or usefulness of something to a stakeholder within a context. Value can be seen as potential or realized returns, gains, and improvements. It is also possible to have a decrease in value in the form of losses, risks, and costs. Value can be tangible or intangible. Tangible value is directly measurable. Tangible value often has a significant monetary component. Intangible value is measured indirectly. Intangible value often has a significant motivational component, such as a company's reputation or employee morale. In some cases, value can be assessed in absolute terms, but in many cases is assessed in relative terms: one solution option is more valuable than another from the perspective of a given set of stakeholders.
|  | Context | The circumstances that influence, are influenced by, and provide understanding of the change. Changes occur within a context. The context is everything relevant to the change that is within the environment. Context may include attitudes, behaviours, beliefs, competitors, culture, demographics, goals, governments, infrastructure, languages, losses, processes, products, projects, sales, seasons, terminology, technology, weather, and any other element meeting the definition.
2.2 | Key Terms | Business Analysis | the practice of enabling change in an enterprise by defining needs and recommending solutions that deliver value to stakeholders.
|  | Business Analysis Information | sets of information that business analysts analyze, transform, and report. It is information of any kind—at any level of detail—that is used as an input to, or is an output of, business analysis work
|  | Design | A Design is a usable representation of a solution. Design focuses on understanding how value might be realized by a solution if it is built.
|  | Enterprise | An enterprise is a system of one or more organizations and the solutions they use to pursue a shared set of common goals.
|  | Organization | An autonomous group of people under the management of a single individual or board, that works towards common goals and objectives.
|  | Plan | A plan is a proposal for doing or achieving something.
|  | Requirement | A requirement is a usable representation of a need.
|  | Risk | Risk is the effect of uncertainty on the value of a change, a solution, or the enterprise.
2.3 | Requirements Classification Schema | Business requirements | statements of goals, objectives, and outcomes that describe why a change has been initiated.
|  | Stakeholder requirements | describe the needs of stakeholders that must be met in order to achieve the business requirements. They may serve as a bridge between business and solution requirements.
|  | Solution requirements | describe the capabilities and qualities of a solution that meets the stakeholder requirements.
|  |  | functional requirements | 功能性需求
|  |  | non-functional requirements or quality of service requirements | 非功能性需求
|  | Transition requirements | describe the capabilities that the solution must have and the conditions the solution must meet to facilitate transition from the current state to the future state. | 转换需求。
2.4 | Stakeholders | Business Analyst
Customer
|  | Domain Subject Matter Expert | managers, process owners, legal staff, consultants, and others. | 领域主题专家
End User
|  | Implementation Subject Matter Expert | project librarian, change manager, configuration manager, solution architect, developer, database administrator, information architect, usability analyst, trainer, and organizational change consultant. | 实施主题专家
|  | Operational Support | day-to-day management and maintenance of a system or product
|  | Project Manager | project lead, technical lead, product manager, and team leader.
|  | Regulator | government, regulatory bodies, and auditor.
|  | Sponsor | executive and project sponsor
|  | Supplier | providers, vendors, and consultants
|  | Tester | quality assurance analyst
2.5 | Requirements and Designs | Requirements | Requirements are focused on the need
|  | Designs | Designs are focused on the solution
Note on D12: chloroplast: autonomous: 自治的
Note on D32: chloroplast: 质量保证分析师

## chapter3
章节 | 标题 | 概念 |  |  | 理解
3.1 | Plan Business Analysis Approach | Purpose |  | define an appropriate method to conduct business analysis activities | 1. align to the overall goals of the change 2. coordinate the business analysis tasks with the activities and deliverables of the overall change 3. include tasks to manage any risks that could reduce the quality of business analysis deliverables or impede task efficiency 4. leverage approaches and select techniques and tools that have historically worked well
|  | Inputs |  | Needs | the business analysis approach is shaped by the problem or opportunity faced by the organization. It is necessary to consider what is known about the need at the time of planning, while acknowledging that understanding evolves throughout business analysis activities.
|  | Outputs |  | Business Analysis Approach | identifies the business analysis approach and activities that will be performed across an initiative including who will perform the activities, the timing and sequencing of the work, the deliverables that will be produced and the business analysis techniques that may be utilized. The remaining outputs of the Business Analysis Planning and Monitoring knowledge area may be integrated into an overall approach or be independent based upon methodology, organization, and perspective.
3.2 | Plan Stakeholder Engagement | Purpose |  | plan an approach for establishing and maintaining effective working relationships with the stakeholders.
|  | Inputs |  | Needs | understanding the business need and the parts of the enterprise that it affects helps in the identification of stakeholders.
|  |  | 3.1 | Business Analysis Approach | incorporating the overall business analysis approach into the stakeholder analysis, collaboration, and communication approaches is necessary to ensure consistency across the approaches.
|  | Outputs |  | Stakeholder Engagement Approach | contains a list of the stakeholders, their characteristics which were analyzed, and a listing of roles and responsibilities for the change. It also identifies the collaboration and communication approaches the business analyst will utilize during the initiative.
3.3 | Plan Business Analysis Governance | Purpose |  | to define how decisions are made about requirements and designs, including reviews, change control, approvals, and prioritization.
|  | Inputs | 3.1 | Business Analysis Approach | incorporating the overall business analysis approach into the governance approach is necessary to ensure consistency across the approaches.
|  |  | 3.2 | Stakeholder Engagement Approach | identifying stakeholders and understanding their communication and collaboration needs is useful in determining their participation in the governance approach. The engagement approach may be updated based on the completion of the governance approach.
|  | Outputs |  | Governance Approach | identifies the stakeholders who will have the responsibility and authority to make decisions about business analysis work including who will be responsible for setting priorities and who will approve changes to business analysis information. It also defines the process that will be utilized to manage requirement and design changes across the initiative.
3.4 | Plan Business Analysis Information Management | Purpose |  | to develop an approach for how business analysis information will be stored and accessed.
|  | Inputs | 3.1 | Business Analysis Approach | incorporating the overall business analysis approach into the information management approach is necessary to ensure consistency across the approaches.
|  |  | 3.2 | Stakeholder Engagement Approach | identifying stakeholders and understanding their communication and collaboration needs is useful in determining their specific information management needs.
|  |  | 3.3 | Governance Approach | defines how business analysts manage changes to requirements and designs, how decisions and approvals for business analysis deliverables will be made, and how priorities will be set.
|  | Outputs |  | Information Management Approach | includes the defined approach for how business analysis information will be stored, accessed, and utilized during the change and after the change is complete.
3.5 | Identify Business Analysis Performance Improvements | Purpose |  | to assess business analysis work and to plan to improve processes where required. | Performance analysis should occur throughout an initiative. Once potential performance improvements are identified, they become guidelines for the next time a task is executed.
|  | Inputs | 3.1 | Business Analysis Approach | identifies business analysis deliverables that will be produced, activities that will need to be performed (including when they will be performed and who will be performing them), and techniques that will be used.
|  |  |  | Performance Objectives (external): | describe the desired performance outcomes that an enterprise or organization is hoping to achieve.
|  | Outputs |  | Business Analysis Performance Assessment | includes a comparison of planned versus actual performance, identifying the root cause of variances from the expected performance, proposed approaches to address issues, and other findings to help understand the performance of business analysis processes.
Note on F10: chloroplast: incorporating: 合并

## chapter4
章节 | 标题 | 概念 |  |  | 理解
4.1 | Prepare for Elicitation | Purpose |  | to understand the scope of the elicitation activity, select appropriate techniques, and plan for (or procure) appropriate supporting materials and resources.
|  | Inputs |  | Needs | guides the preparation in terms of the scope and purpose of elicitation activities. Elicitation can be used to discover the needs, but in order to get started there must be some need that exists—even if it has not yet been fully elicited or understood.
|  |  | 3.2 | Stakeholder Engagement Approach | understanding stakeholders' communication and collaboration needs helps plan and prepare appropriate and effective elicitation events.
|  | Outputs |  | Elicitation Activity Plan | used for each elicitation activity. It includes logistics, scope of the elicitation activity, selected techniques, and supporting materials.
4.2 | Conduct Elicitation | Purpose |  | to draw out, explore, and identify information relevant to the change. | 1.Collaborative 2. Research 3. Experiments
|  | Inputs | 4.1 | Elicitation Activity Plan | includes the planned elicitation activities and techniques, activity logistics (for example, date, time, location, resources,agenda), scope of the elicitation activity, and available sources of background information.
|  | Outputs |  | Elicitation Results (unconfirmed) | captured information in a format that is specific to the elicitation activity.
4.3 | Confirm Elicitation Results | Purpose |  | check the information gathered during an elicitation session for accuracy and consistency with other information.
|  | Inputs | 4.2 | Elicitation Results (unconfirmed) | captured information in a format that is specific to the elicitation activity.
|  | Outputs |  | Elicitation Results (confirmed) | integrated output that the business analyst and other stakeholders agree correctly reflects captured information and confirms that it is relevant and useful as an input to further work.
4.4 | Communicate Business Analysis Information | Purpose |  | to ensure stakeholders have a shared understanding of business analysis information.
|  | Inputs |  | Business Analysis Information | any kind of information at any level of detail that is used as an input or output of business analysis work. Business analysis information becomes an input for this task when the need is discovered to communicate the information to additional stakeholders.
|  |  | 3.2 | Stakeholder Engagement Approach | describes stakeholder groups, roles, and general needs regarding communication of business analysis information.
|  | Outputs |  | Business Analysis Information (communicated) | business analysis information is considered communicated when the target stakeholders have reached an understanding of its content and implications.
4.5 | Manage Stakeholder Collaboration | Purpose |  | to encourage stakeholders to work towards a common goal.
|  | Inputs | 3.2 | Stakeholder Engagement Approach | describes the types of expected engagement with stakeholders and how they might need to be managed.
|  |  | 3.6 | Business Analysis Performance Assessment | provides key information about the effectiveness of business analysis tasks being executed, including those focused on stakeholder engagement.
|  | Outputs |  | Stakeholder Engagement | willingness from stakeholders to engage in business analysis activities and interact with the business analyst when necessary.
Note on E2: chloroplast: procure: 获得
Note on E6: chloroplast: draw out: 提取
Note on F7: chloroplast: agenda: 议程

## chapter5
章节 | 标题 | 概念 |  | 理解
5.1 | Trace Requirements | Purpose | to ensure that requirements and designs at different levels are aligned to one another, and to manage the effects of change to one level on related requirements. | 1. faster and simpler impact analysis 2. more reliable discovery of inconsistencies and gaps in requirements 3. deeper insights into the scope and complexity of a change 4. reliable assessment of which requirements have been addressed and which have not
|  | Inputs | Requirements | may be traced to other requirements (including goals, objectives, business requirements, stakeholder requirements, solution requirements, and transition requirements), solution components, visuals, business rules, and other work products.
|  |  | Designs | may be traced to other requirements, solution components, and other work products.
|  | Outputs | Requirements (traced) | clearly defined relationships to other requirements, solution components, or releases, phases, or iterations, within a solution scope, such that coverage and the effects of change are clearly identifiable.
|  |  | Designs (traced) | clearly defined relationships to other requirements, solution components, or releases, phases, or iterations, within a solution scope, such that coverage and the effects of change are clearly identifiable.
5.2 | Maintain Requirements | Purpose | to retain requirement accuracy and consistency throughout and beyond the change during the entire requirements life cycle, and to support reuse of requirements in other solutions.
|  | Inputs | Requirements | include goals, objectives, business requirements, stakeholder requirements, solution requirements, and transition requirements. These should be maintained throughout their life cycle.
|  |  | Designs | can be maintained throughout their life cycle, as needed.
|  | Outputs | Requirements (maintained) | defined once and available for long-term usage by the organization. They may become organizational process assets or be used in future initiatives. In some cases, a requirement that was not approved or implemented may be maintained for a possible future initiative.
|  |  | Designs (maintained) | may be reusable once defined. For example, as a selfcontained component that can be made available for possible future use.
5.3 | Prioritize Requirements | Purpose | to rank requirements in the order of relative importance.
|  | Inputs | Requirements | any requirements in the form of text, matrices, or diagrams that are ready to prioritize.
|  |  | Designs | any designs in the form of text, prototypes, or diagrams that are ready to prioritize.
|  | Outputs | Requirements (prioritized) | prioritized or ranked requirements are available for additional work, ensuring that the highest valued requirements are addressed first.
|  |  | Designs (prioritized) | prioritized or ranked designs are available for additional work, ensuring that the highest valued designs are addressed first.
5.4 | Assess Requirements Changes | Purpose | to evaluate the implications of proposed changes to requirements and designs.
|  | Inputs | Proposed Change | can be identified at any time and impact any aspect of business analysis work or deliverables completed to date. There are many triggers for a proposed change including business strategy changes, stakeholders, legal requirements, or regulatory changes.
|  |  | Requirements | may need to be assessed to identify the impact of a proposed modification.
|  |  | Designs | may need to be assessed to identify the impact of a proposed modification.
|  | Outputs | Requirements Change Assessment | the recommendation to approve, modify, or deny a proposed change to requirements.
|  |  | Designs Change Assessment | the recommendation to approve, modify, or deny a proposed change to one or more design components.
5.5 | Approve Requirements | Purpose | to obtain agreement on and approval of requirements and designs for business analysis work to continue and/or solution construction to proceed.
|  | Inputs | Requirements (verified) | a set of requirements that have been verified to be of sufficient quality to be used as a reliable body of work for further specification and development.
|  |  | Designs | a set of designs that have been determined as ready to be used for further specification and development.
|  | Outputs | Requirements (approved) | requirements which are agreed to by stakeholders and are ready for use in subsequent business analysis efforts.
|  |  | Designs (approved) | designs which are agreed to by stakeholders and are ready for use in subsequent business analysis or solution development efforts.
Note on E17: chloroplast: implications: 影响
Note on E18: chloroplast: 提出的变更

## chapter6
章节 | 标题 | 概念 |  |  | 理解
6.1 | Analyze Current State | Purpose |  | to understand the reasons why an enterprise needs to change some aspect of how it operates and what would be directly or indirectly affected by the change.
|  | Inputs | 4.3 | Elicitation Results (confirmed) | used to define and understand the current state.
|  |  |  | Needs | the problem or opportunity faced by an enterprise or organization often launches business analysis work to better understand these needs.
|  | Outputs |  | Current State Description | the context of the enterprise’s scope, capabilities, resources, performance, culture, dependencies, infrastructure, external influences, and significant relationships between these elements.
|  |  |  | Business Requirements | the problem, opportunity, or constraint which is defined based on an understanding of the current state.
6.2 | Define Future State | Purpose |  | to determine the set of necessary conditions to meet the business need.
|  | Inputs |  | Business Requirements | the problems, opportunities, or constraints that the future state will address.
|  | Outputs |  | Business Objectives | the desired direction that the business wishes to pursue in order to achieve the future state.
|  |  |  | Future State Description | the future state description includes boundaries of the proposed new, removed, and modified components of the enterprise and the potential value expected from the future state. The description might include the desired future capabilities, policies, resources, dependencies, infrastructure, external influences, and relationships between each element.
|  |  |  | Potential Value | the value that may be realized by implementing the proposed future state.
6.3 | Assess Risks | Purpose |  | to understand the undesirable consequences of internal and external forces on the enterprise during a transition to, or once in, the future state. An understanding of the potential impact of those forces can be used to make a recommendation about a course of action. | 1. possible consequences if the risk occurs 2. impact of those consequences 3. likelihood of the risk 4. potential time frame when the risk might occur
|  | Inputs | 6.2 | Business Objectives | describing the desired direction needed to achieve the future state can be used to identify and discuss potential risks.
|  |  | 4.3 | Elicitation Results (confirmed) | an understanding of what the various stakeholders perceive as risks to the realization of the desired future state.
|  |  |  | Influences (internal and external) | factors inside of the enterprise (internal) and factors outside of the enterprise (external) which will impact the realization of the desired future state.
|  |  | 6.2 | Potential Value | describing the value to be realized by implementing the proposed future state provides a benchmark against which risks can be assessed.
|  |  | 5.3 | Requirements (prioritized) | depending on their priority, requirements will influence the risks to be defined and understood as part of solution realization.
|  |  | 5.3 | Designs (prioritized)
|  | Outputs |  | Risk Analysis Results | an understanding of the risks associated with achieving the future state, and the mitigation strategies which will be used to prevent those risks, reduce the impact of the risk, or reduce the likelihood of the risk occurring.
6.4 | Define Change Strategy | Purpose |  | to develop and assess alternative approaches to the change, and then select the recommended approach. | 1. context of the change 2. identified alternative change strategies 3. justification for why a particular change strategy is the best approach 4. investment and resources required to work toward the future state 5. how the enterprise will realize value after the solution is delivered 6. key stakeholders in the change 7. transition states along the way
|  | Inputs | 6.1 | Current State Description | provides context about the current state, and includes assessments of internal and external influences to the enterprise under consideration.
|  |  | 6.2 | Future State Description | provides context about the desired future state.
|  |  | 6.3 | Risk Analysis Results | describe identified risks and exposure of each risk.
|  |  | 3.2 | Stakeholder Engagement Approach | understanding stakeholders' communication and collaboration needs can help identify change-related activities that need to be included as part of the change strategy.
|  | Outputs |  | Change Strategy | the approach that the organization will follow to guide change
|  |  |  | Solution Scope | the solution scope that will be achieved through execution of the change strategy
Note on F9: chloroplast: pursue: 追求
Note on F11: chloroplast: proposed: 提议，建议
Note on F14: chloroplast: 理解不同干系人对实现预期未来状态的风险的理解。
Note on F20: chloroplast: transition states along the way: 过度状态
Note on F23: chloroplast: 描述已识别的风险和每个风险的暴露程度

## chapter7
章节 | 标题 | 概念 |  |  | 理解
7.1 | Specify and Model Requirements | Purpose |  | to analyze, synthesize, and refine elicitation results into requirements and designs
|  | Inputs | 4.2，4.3 | Elicitation Results (any state) | modelling can begin with any elicitation result and may lead to the need for more elicitation to clarify or expand upon requirements. Elicitation and modelling may occur sequentially, iteratively, or concurrently.
|  | Outputs |  | Requirements (specified and modelled) | any combination of requirements and/or designs in the form of text, matrices, and diagrams.
7.2 | Verify Requirements | Purpose |  | to ensure that requirements and designs specifications and models meet quality standards and are usable for the purpose they serve.
|  | Inputs | 7.1 | Requirements (specified and modelled) | any requirement, design, or set of those may be verified to ensure that text is well structured and that matrices and modelling notation are used correctly.
|  | Outputs |  | Requirements (verified) | a set of requirements or designs that is of sufficient quality to be used as a basis for further work.
7.3 | Validate Requirements | Purpose |  | to ensure that all requirements and designs align to the business requirements and support the delivery of needed value.
|  | Inputs | 7.1 | Requirements (specified and modelled) | any types of requirements and designs can be validated. Validation activities may begin before requirements are completely verified. However, validation activities cannot be completed before requirements are completely verified.
|  | Outputs |  | Requirements (validated) | validated requirements and designs are those that can be demonstrated to deliver benefit to stakeholders and align with the business goals and objectives of the change. If a requirement or design cannot be validated, it either does not benefit the organization, does not fall within the solution scope, or both.
7.4 | Define Requirements Architecture | Purpose |  | to ensure that the requirements collectively support one another to fully achieve the objectives.
|  | Inputs | 3.4 | Information Management Approach | defines how the business analysis information (including requirements and models) will be stored and accessed.
|  |  |  | Requirements (any state) | every requirement should be stated once, and only once, and incorporated into the requirements architecture so that the entire set may be evaluated for completeness.
|  |  | 6.4 | Solution Scope | must be considered to ensure the requirements architecture is aligned with the boundaries of the desired solution.
|  | Outputs |  | Requirements Architecture | the requirements and the interrelationships among them, as well as any contextual information that is recorded.
7.5 | Define Solution Options | Purpose |  | to define the solution approach, identify opportunities to improve the business, allocate requirements across solution components, and represent design options that achieve the desired future state.
|  | Inputs | 6.4 | Change Strategy | describes the approach that will be followed to transition to the future state. This may have some impact on design decisions in terms of what is feasible or possible.
|  |  | 5.3, 7.3 | Requirements (validated, prioritized) | only validated requirements are considered in design options. Knowing the requirement priorities aids in the suggestion of reasonable design options. Requirements with the highest priorities might deserve more weight in choosing solution components to best meet them as compared to lower priority requirements.
|  |  | 7.4 | Requirements Architecture | the full set of requirements and their relationships is important for defining design options that can address the holistic set of requirements.
|  | Outputs |  | Design Options | describe various ways to satisfy one or more needs in a context. They may include solution approach, potential improvement opportunities provided by the option, and the components that define the option.
7.6 | Analyze Potential Value and Recommend Solution | Purpose |  | to estimate the potential value for each design option and to establish which one is most appropriate to meet the enterprise’s requirements.
|  | Inputs | 6.2 | Potential Value | can be used as a benchmark against which the value delivered by a design can be evaluated.
|  |  | 7.5 | Design Options | need to be evaluated and compared to one another to recommend one option for the solution.
|  | Outputs |  | Solution Recommendation | identifies the suggested, most appropriate solution based on an evaluation of all defined design options. The recommended solution should maximize the value provided to the enterprise.
Note on E12: chloroplast: collectively: 共同的
Note on F16: chloroplast: contextual: 上下文
Note on F18: chloroplast: feasible: 可行的
Note on F20: chloroplast: holistic: 整体

## chapter8
章节 | 标题 | 概念 |  |  | 理解
8.1 | Measure Solution Performance | Purpose |  | to define performance measures and use the data collected to evaluate the effectiveness of a solution in relation to the value it brings.
|  | Inputs | 6.2 | Business Objectives | the measurable results that the enterprise wants to achieve. Provides a benchmark against which solution performance can be assessed.
|  |  |  | Implemented Solution (external) | a solution (or component of a solution) that exists in some form. It may be an operating solution, a prototype, or a pilot or beta solution.
|  | Outputs |  | Solution Performance Measures | measures that provide information on how well the solution is performing or potentially could perform.
8.2 | Analyze Performance Measures | Purpose |  | to provide insights into the performance of a solution in relation to the value it brings.
|  | Inputs | 6.2 | Potential Value | describes the value that may be realized by implementing the proposed future state. It can be used as a benchmark against which solution performance can be evaluated.
|  |  | 8.1 | Solution Performance Measures | measures and provides information on how well the solution is performing or potentially could perform.
|  | Outputs |  | Solution Performance Analysis | results of the analysis of measurements collected and recommendations to solve performance gaps and leverage opportunities to improve value.
8.3 | Assess Solution Limitations | Purpose |  | to determine the factors internal to the solution that restrict the full realization of value.
|  | Inputs |  | Implemented Solution (external) | a solution that exists. The solution may or may not be in operational use; it may be a prototype. The solution must be in use in some form in order to be evaluated.
|  |  | 8.2 | Solution Performance Analysis | results of the analysis of measurements collected and recommendations to solve for performance gaps and leverage opportunities to improve value.
|  | Outputs |  | Solution Limitation | a description of the current limitations of the solution including constraints and defects.
8.4 | Assess Enterprise Limitations | Purpose |  | to determine how factors external to the solution are restricting value realization.
|  | Inputs | 6.1 | Current State Description | the current internal environment of the solution including the environmental, cultural, and internal factors influencing the solution limitations.
|  |  |  | Implemented (or Constructed) Solution (external) | a solution that exists. The solution may or may not be in operational use; it may be a prototype. The solution must be in use in some form in order to be evaluated.
|  |  | 8.2 | Solution Performance Analysis | results of the analysis of measurements collected and recommendations to solve performance gaps and leverage opportunities to improve value.
|  | Outputs |  | Enterprise Limitation | a description of the current limitations of the enterprise including how the solution performance is impacting the enterprise.
8.5 | Recommend Actions to Increase Solution Value | Purpose |  | to understand the factors that create differences between potential value and actual value, and to recommend a course of action to align them.
|  | Inputs | 8.3 | Solution Limitation | a description of the current limitations of the solution including constraints and defects.
|  |  | 8.4 | Enterprise Limitation | a description of the current limitations of the enterprise including how the solution performance is impacting the enterprise.
|  | Outputs |  | Recommended Actions | recommendation of what should be done to improve the value of the solution within the enterprise.
Note on F13: chloroplast: defects: 缺点

## chapter9
章节 | 分类 | 标题 | 概念 |  | 理解
9.1 Analytical Thinking and Problem Solving | 9.1.1 | Creative Thinking | Purpose | Thinking creatively and helping others to apply creative thinking helps business analysts to be effective in generating new ideas, approaches, and alternatives to problem solving and opportunities
| 9.1.2 | Decision Making | Purpose | Business analysts must be effective in understanding the criteria involved in making a decision, and in assisting others to make better decisions.
| 9.1.3 | Learning | Purpose | The ability to quickly absorb new and different types of information and also modify and adapt existing knowledge allows business analysts to work effectively in rapidly changing and evolving environments.
| 9.1.4 | Problem Solving | Purpose | Business analysts define and solve problems in order to ensure that the real, underlying root cause of a problem is understood by all stakeholders and that solution options address that root cause.
| 9.1.5 | Systems Thinking | Purpose | Understanding how the people, processes, and technology within an organization interact allows business analysts to understand the enterprise from a holistic point of view.
| 9.1.6 | Conceptual Thinking | Purpose | Business analysts routinely receive large amounts of detailed and potentially disparate information. They apply conceptual thinking skills to find ways to understand how that information fits into a larger picture and what details are important, and to connect seemingly abstract information.
| 9.1.7 | Visual Thinking | Purpose | The ability to communicate complex concepts and models into understandable visual representations allows business analysts to engage stakeholders and help them understand the concepts being presented.
9.2 Behavioural Characteristics | 9.2.1 | Ethics | Purpose | Behaving ethically and thinking of ethical impacts on others allows business analysts to earn the respect of the stakeholders. The ability to recognize when a proposed solution or requirement may present ethical difficulties to an organization or its stakeholders is an important consideration that business analysts can use to help reduce exposure to risk.
| 9.2.2 | Personal Accountability | Purpose | Personal accountability is important for a business analyst because it ensures business analysis tasks are completed on time and to the expectations of colleagues and stakeholders. It enables the business analyst to establish credibility by ensuring that business analysis efforts meet the needs of the business.
| 9.2.3 | Trustworthiness | Purpose | Earning the trust of stakeholders helps business analysts elicit business analysis information around sensitive issues and enables them to help stakeholders have confidence that their recommendations will be evaluated properly and fairly.
| 9.2.4 | Organization and Time Management | Purpose | Organization and time management skills help business analysts perform tasks effectively and use work time efficiently.
| 9.2.5 | Adaptability | Purpose | Business analysts frequently work in rapidly changing environments and with a variety of stakeholders. They adjust their behavioural style and method of approach to increase their effectiveness when interacting with different stakeholders, organizations, and situations.
9.3 Business Knowledge | 9.3.1 | Business Acumen | Purpose | Business analysis requires an understanding of fundamental business principles and best practices in order to ensure they are considered as solutions are reviewed.
| 9.3.2 | Industry Knowledge | Purpose | Industry knowledge provides the business analyst with an understanding of current practices and activities within an industry, and similar processes across industries.
| 9.3.3 | Organization Knowledge | Purpose | Organization knowledge provides an understanding of the management structure and business architecture of the enterprise.
| 9.3.4 | Solution Knowledge | Purpose | Solution knowledge allows business analysts to leverage their understanding of existing departments, environments, or technology to efficiently identify the most effective means of implementing a change.
| 9.3.5 | Methodology Knowledge | Purpose | Understanding the methodologies used by the organization provides the business analyst with information regarding context, dependencies, opportunities, and constraints used when developing a business analysis approach.
9.4 Communication Skills | 9.4.1 | Verbal Communication | Purpose | Business analysts use verbal communication to convey ideas, concepts, facts, and opinions to a variety of stakeholders.
| 9.4.2 | Non-Verbal Communication | Purpose | Non-verbal communication skills enable the effective sending and receiving of messages through—but not limited to—body movement, posture, facial expressions, gestures, and eye contact.
| 9.4.3 | Written Communication | Purpose | Business analysts use written communication to to convey ideas, concepts, facts, and opinions to variety of stakeholders.
| 9.4.4 | Listening | Purpose | Effective listening allows the business analyst to accurately understand information that is communicated verbally.
9.5 Interaction Skills | 9.5.1 | Facilitation | Purpose | Business analysts facilitate interactions between stakeholders in order to help them make a decision, solve a problem, exchange ideas and information, or reach an agreement regarding the priority and the nature of requirements. The business analyst may also facilitate interactions between stakeholders for the purposes of negotiation and conflict resolution.
| 9.5.2 | Leadership and Influencing | Purpose | Business analysts use leadership and influencing skills when guiding stakeholders during the investigation of business analysis information and solution options. They build consensus and encourage stakeholder support and collaboration during change.
| 9.5.3 | Teamwork | Purpose | Teamwork skills allow business analysts to work productively with team members, stakeholders, and any other vested partners so that solutions can be effectively developed and implemented.
| 9.5.4 | Negotiation and Conflict Resolution | Purpose | Business analysts occasionally mediate negotiations between stakeholders in order to reach a common understanding or an agreement. During this process, business analysts help resolve conflicts and differences of opinion with the intent of maintaining and strengthening working relationships among stakeholders and team members.
| 9.5.5 | Teaching | Purpose | Teaching skills help business analysts effectively communicate business analysis information, concepts, ideas, and issues. They also help ensure that information is understood and retained by stakeholders.
9.6 Tools and Technology | 9.6.1 | Office Productivity Tools and Technology | Purpose | Business analysts use office productivity tools and technology to document and track information and artifacts.
| 9.6.2 | Business Analysis Tools and Technology | Purpose | Business analysts use a variety of tools and technology to model, document, and manage outputs of business analysis activities and deliverables to stakeholders.
| 9.6.3 | Communication Tools and Technology | Purpose | Business analysts use communication tools and technology to perform business analysis activities, manage teams, and collaborate with stakeholders.
Note on A2: chloroplast: Analytical: 善于分析的
Note on E6: chloroplast: holistic: 整体的
Note on C7: chloroplast: Conceptual: 概念
Note on E7: chloroplast: disparate：不同的，不相干的
Note on C9: chloroplast: 行为准则
Note on C11: chloroplast: 可信赖
Note on C13: chloroplast: 适应性
Note on C14: chloroplast: 商业头脑
Note on C18: chloroplast: Methodology: 方法论
Note on C19: chloroplast: 语言交流
Note on E20: chloroplast: 体动作、姿势、面部表情、手势和眼神交流
Note on C23: chloroplast: 增强
Note on C26: chloroplast: 谈判与冲突管理

## chapter10
章节 | 标题 | 概念 |  |  | 理解
10.1 | Acceptance and Evaluation Criteria | Purpose |  | Acceptance criteria are used to define the requirements, outcomes, or conditions that must be met in order for a solution to be considered acceptable to key stakeholders. Evaluation criteria are the measures used to assess a set of requirements in order to choose between multiple solutions.
|  | Description |  | Acceptance and evaluation criteria define measures of value attributes to be used for assessing and comparing solutions and alternative designs.
|  | Elements | Value Attributes
|  |  | Assessment | 1. Testability 2. Measures
10.2 | Backlog Management | Purpose |  | The backlog is used to record, track, and prioritize remaining work items.
|  | Description |  | A backlog occurs when the volume of work items to be completed exceeds the capacity to complete them. In a managed backlog, the items at the top have the highest business value and the highest priority. These are normally the next items to be selected to be worked on.
|  | Elements | Items in the Backlog | An item is added to the backlog if it has value to a stakeholder
|  |  | Prioritization | Items in the backlog are prioritized relative to each other.
|  |  | Estimation | Items near the top of the backlog are usually described in more detail, with a correspondingly accurate estimate about their relative size and complexity that would help to determine the cost and effort to complete them.
Managing Changes to the Backlog
10.3 | Balanced Scorecard | Purpose |  | The balanced scorecard is used to manage performance in any business model, organizational structure, or business process.
|  | Description |  | The balanced scorecard is a strategic planning and management tool used to measure organizational performance beyond the traditional financial measures. The balanced scorecard is composed of four dimensions: 1. Learning and Growth 2. Business Process 3. Customer, and 4. Financial
|  | Elements | Learning and Growth Dimension | measures regarding employee training and learning, product and service innovation, and corporate culture.
|  |  | Business Process Dimension | how well the enterprise is operating and if their products meet customer needs.
|  |  | Customer Dimension | metrics on customer focus, satisfaction and delivery of value. These metrics capture how well customer needs are met, how satisfied they are with products and services, whether the delivery of those products and services meet their quality expectations, and their overall experience with the enterprise.
|  |  | Financial Dimension | identifies what is financially necessary to realize the strategy. (profitability, revenue growth, and added economic value).
|  |  | Measures or Indicators | 1. lagging indicators that provide results of actions already taken 2. leading indicators that provide information about future performance.
10.4 | Benchmarking and Market Analysis | Purpose |  | conducted to improve organizational operations, increase customer satisfaction, and increase value to stakeholders.
|  | Description |  | 1. Benchmark studies are conducted to compare organizational practices against the best-in-class practices. 2. Market analysis involves researching customers in order to determine the products and services that they need or want, the factors that influence their decisions to purchase, and the competitors that exist in the market.
|  | Elements | Benchmarking
Market Analysis
10.5 | Brainstorming | Purpose |  | to foster creative thinking about a problem. The aim of brainstorming is to produce numerous new ideas, and to derive from them themes for further analysis.
|  | Description |  | Brainstorming is a technique intended to produce a broad or diverse set of options.
|  | Elements | Preparation
Session
Wrap-up
10.6 | Business Capability Analysis | Purpose |  | Business capability analysis provides a framework for scoping and planning by generating a shared understanding of outcomes, identifying alignment with strategy, and providing a scope and prioritization filter.
|  | Description |  | Business capability analysis describes what an enterprise, or part of an enterprise, is able to do.
|  | Elements | Capabilities | Capabilities are the abilities of an enterprise to perform or transform something that helps achieve a business goal or objective.
|  |  | Using Capabilities | Capabilities impact value through increasing or protecting revenue, reducing or preventing cost, improving service, achieving compliance, or positioning the company for the future.
|  |  | Performance Expectations | Capabilities can be assessed to identify explicit performance expectations. When a capability is targeted for improvement, a specific performance gap can be identified.
|  |  | Risk Model | Capabilities alone do not have risks—the risks are in the performance of the capability, or in the lack of performance. 1. business risk 2. technology risk 3. organizational risk 4. market risk
|  |  | Strategic Planning | Business capabilities for the current state and future state of an enterprise can be used to determine where that enterprise needs to go in order to accomplish its strategy.
Capability Maps
10.7 | Business Cases | Purpose |  | A business case provides a justification for a course of action based on the benefits to be realized by using the proposed solution, as compared to the cost, effort, and other considerations to acquire and live with that solution.
|  | Description |  | A business case captures the rationale for undertaking a change. The business case provides sufficient detail to inform and request approval without providing specific intricacies about the method and/or approach to the implementation. A business case is used to: 1. define the need 2. determine the desired outcomes 3. assess constraints, assumptions, and risks, and 4. recommend a solution
|  | Elements | Need Assessment | The need is the driver for the business case. The need assessment identifies the problem or the potential opportunity.
|  |  | Desired Outcomes | The desired outcomes describe the state which should result if the need is fulfilled.
|  |  | Assess Alternatives | The business case identifies and assesses various alternative solutions. Each alternative should be assessed in terms of: 1. Scope: Scope statements clearly define what will be included and what will be excluded. 2. Feasibility: It includes organizational knowledge, skills, and capacity, as well as technical maturity and experience in the proposed technologies. 3. Assumptions, Risks, and Constraints: Assumptions are agreed-to facts that may have influence on the initiative. Constraints are limitations that may restrict the possible alternatives. Risks are potential problems that may have a negative impact on the solution. 4. Financial Analysis and Value Assessment: includes an estimate of the costs to implement and operate the alternative, as well as a quantified financial benefit from implementing the alternative.
|  |  | Recommended Solution | describes the most desirable way to solve the problem or leverage the opportunity.
10.8 | Business Model Canvas | Purpose |  | A business model canvas describes how an enterprise creates, delivers, and captures value for and from its customers.
|  | Description |  | A business model canvas is comprised of nine building blocks that describe how an organization intends to deliver value: • Key Partnerships, • Key Activities, • Key Resources, • Value Proposition, • Customer Relationships, • Channels, • Customer Segments, • Cost Structure, and • Revenue Streams.
|  | Elements | Key Partnerships | Key partnerships frequently involve some degree of sharing of proprietary information, including technologies.
|  |  | Key Activities | Key activities are those that are critical to the creation, delivery, and maintenance of value. 1. Value-add 2. Non-value-add 3. Business non-value-add
|  |  | Key Resources | Resources are the assets needed to execute a business model. 1. Physical 2. Financial 3. Intellectual 4. Human
|  |  | Value Proposition | A value proposition represents what a customer is willing to exchange for having their needs met.
|  |  | Customer Relationships | customer relationships are classified as customer acquisition and customer retention.
|  |  | Channels | Channels are the different ways an enterprise interacts with and delivers value to its customers.
|  |  | Customer Segments | Customer segments group customers with common needs and attributes so that the enterprise can more effectively and efficiently address the needs of each segment.
Cost Structure
|  |  | Revenue Streams | revenue comes into an enterprise from each customer segment in exchange for the realization of a value proposition. 1. Licensing or Subscription fees 2. Transaction or Usage fees 3. Sales 4. Lending, Renting, or Leasing
10.9 | Business Rules Analysis | Purpose |  | to identify, express, validate, refine, and organize the rules that shape day-to-day business behaviour and guide operational business decision making.
|  | Description |  | Business policies and rules guide the day-to-day operation of the business and its processes, and shape operational business decisions.
|  | Elements | Definitional Rules | Definitional rules shape concepts, or produce knowledge or information.
|  |  | Behavioural Rules | Behavioural rules are people rules–even if the behaviour is automated.
10.10 | Collaborative Games | Purpose |  | encourage participants in an elicitation activity to collaborate in building a joint understanding of a problem or a solution.
|  | Description |  | Collaborative games refer to several structured techniques inspired by game play and are designed to facilitate collaboration.
|  | Elements | Game Purpose | to develop a better understanding of a problem or to stimulate creative solutions
Process
Outcome
|  |  | Examples of Collaborative Games | 1. Product Box: Used to help identify features of a product that help drive interest in the marketplace. 2. Affinity Map: Used to help identify related or similar features or themes. 3. Fishbowl: Used to identify hidden assumptions or perspectives.
10.11 | Concept Modelling | Purpose |  | is used to organize the business vocabulary needed to consistently and thoroughly communicate the knowledge of a domain.
|  | Description |  | A concept model starts with a glossary, which typically focuses on the core noun concepts of a domain.
|  | Elements | Noun Concepts
|  |  | Verb Concepts | Verb concepts provide basic structural connections between noun concepts.
Other Connections
10.12 | Data Dictionary | Purpose |  | to standardize a definition of a data element and enable a common interpretation of data elements.
|  | Description |  | A data dictionary is used to document standard definitions of data elements, their meanings, and allowable values.
|  | Elements | Data Elements | Data dictionaries describe data element characteristics including the description of the data element in the form of a definition that will be used by stakeholders.
|  |  | Primitive Data Elements | 1. Name 2. Aliases 3. Values/Meanings 4. Description
|  |  | Composite Elements | 1. Sequences 2. Repetitions 3. Optional Elements
10.13 |  | Purpose |  | Data flow diagrams show where data comes from, which activities process the data, and if the output results are stored or utilized by another activity or external entity.
|  | Description |  | Data flow diagrams portray the transformation of data.
|  | Elements | Externals (Entity, Source, Sink) | An external (entity, source, sink) is a person, organization, automated system, or any device capable of producing data or receiving data.
|  |  | Data Store | A data store is a collection of data where data may be read repeatedly and where it can be stored for future use.
|  |  | Process | A process can be a manual or automated activity performed for a business reason. A process transforms the data into an output.
|  |  | Data Flow | The movement of data between an external, a process, and a data store is represented by data flows.
10.14 |  | Purpose |  | is used to improve decision making by finding useful patterns and insights from data.
|  | Description |  | Data mining is an analytic process that examines large amounts of data from different perspectives and summarizes the data in such a way that useful patterns and relationships are discovered. 1. Descriptive 2. Diagnostic 3. Predictive
|  | Elements | Requirements Elicitation | The goal and scope of data mining is established either in terms of decision requirements for an important identified business decision, or in terms of a functional area where relevant data will be mined for domain-specific pattern discovery.
|  |  | Data Preparation: Analytical Dataset | This is generally formed by merging records from multiple tables or sources into a single, wide dataset.
|  |  | Data Analysis | A wide variety of statistical measures are typically applied and visualization tools used to see how data values are distributed, what data is missing, and how various calculated characteristics behave.
Modelling Techniques
|  |  | Deployment | Data mining models can be deployed in a variety of ways, either to support a human decision maker or to support automated decision-making systems.
10.15 | Data Modelling | Purpose |  | describes the entities, classes or data objects relevant to a domain, the attributes that are used to describe them, and the relationships among them to provide a common set of semantics for analysis and implementation.
|  | Description |  | A data model usually takes the form of a diagram that is supported by textual descriptions. 1. Conceptual data model: how the business perceives its information. 2. Logical data model: is an abstraction of the conceptual data model that incorporates rules of normalization to formally manage the integrity of the data and relationships. It is associated with the design of a solution. 3. Physical data model: is used by implementation subject matter experts to describe how a database is physically organized. It addresses concerns like performance, concurrency, and security.
|  | Elements | Entity or Class | In a data model, the organization keeps data on entities (or classes or data objects).
|  |  | Attribute | 1. Name: 2. Values/Meanings 3. Description
|  |  | Relationship or Association | The relationships between entities provide structure for the data model, specifically indicating which entities relate to which others and how.
|  |  | Diagrams | 1. ER 2. UML
|  |  | Metadata | A data model optionally contains metadata describing what the entities represent, when and why they were created or changed, how they should be used, how often they are used, when, and by whom.
10.16 | Decision Analysis | Purpose |  | formally assesses a problem and possible decisions in order to determine the value of alternate outcomes under conditions of uncertainty.
|  | Description |  | Decision analysis examines and models the possible consequences of different decisions about a given problem. Decision analysis approaches use the following activities: 1. Define Problem Statement 2. Define Alternatives 3. Evaluate Alternatives 4. Choose Alternative to Implement 5. Implement Choice tools and techniques: 1. pro versus con considerations 2. force field analysis 3. decision tables 4. decision trees 5. comparison analysis 6. analytical hierarchy process (AHP), 7. totally-partially-not (TPN), 8. multi-criteria decision analysis (MCDA), and 9. computer-based simulations and algorithms.
|  | Elements | Components of Decision Analysis | 1. Decision to be Made or Problem Statement 2. Decision Maker 3. Alternative 4. Decision Criteria
Decision Matrices
|  |  | Decision Trees | A decision tree is a method of assessing the preferred outcome where multiple sources of uncertainty may exist. 1. Decision Nodes: different strategies 2. Chance Nodes: uncertain outcomes 3. Terminator or End Nodes: identify a final outcome of the tree
|  |  | Trade-offs | 1. Elimination of dominated alternatives 2. Ranking objectives on a similar scale
10.17 | Decision Modelling | Purpose |  | shows how repeatable business decisions are made.
|  | Description |  | Decision models show how data and knowledge are combined to make a specific decision.
|  | Elements | Types of Models and Notations
Decision Tables
Decision Trees
|  |  | Decision Requirements Diagrams | 1. Decisions 2. Input Data 3. Business Knowledge Models 4. Knowledge Sources
10.18 | Document Analysis | Purpose |  | is used to elicit business analysis information, including contextual understanding and requirements, by examining available materials that describe either the business environment or existing organizational assets.
|  | Description |  | Document analysis may be used to gather background information in order to understand the context of a business need, or it may include researching existing solutions to validate how those solutions are currently implemented.
|  | Elements | Preparation | Document analysis materials may originate from public or proprietary sources.
|  |  | Document Review and Analysis | 1. Conducting a detailed review of each document’s content and recording relevant notes associated with each topic. 2. Identifying if any notes conflict or are duplicates. 3. Noting any gaps in knowledge in which the findings about certain topics are limited.
|  |  | Record Findings | 1. if the content and level of detail is appropriate for the intended audience 2. if the material should be transformed into visual aids such as graphs, models, process flows, or decision tables in order to help improve understanding
10.19 | Estimation | Purpose |  | is used by business analysts and other stakeholders to forecast the cost and effort involved in pursuing a course of action.
|  | Description |  | Estimation is used to support decision making by predicting attributes
|  | Elements | Methods | 1. Top-down: examining the components at a high level in a hierarchical breakdown. 2. Bottom-up: using the lowest-level elements of a hierarchical breakdown to examine the work in detail and estimate the individual cost or effort, and then summing across all elements to provide an overall estimate. 3. Parametric Estimation: use of a calibrated parametric model of the element attributes being estimated. 4. Rough Order of Magnitude (ROM): a high-level estimate, generally based on limited information, which may have a very wide confidence interval. 5. Rolling Wave: repeated estimates throughout an initiative or project, providing detailed estimates for near-term activities (such as an iteration of the work) extrapolated for the remainder of the initiative or project. 6. Delphi: uses a combination of expert judgment and history 7. PERT
|  |  | Accuracy of the Estimate | The accuracy of an estimate is a measure of uncertainty that evaluates how close an estimate is to the actual value measured later.
|  |  | Sources of Information | 1. Analogous Situations 2. Organization History 3. Expert Judgment
|  |  | Precision and Reliability of Estimates | 1. the precision of the resulting estimate is a measure of agreement between the estimates (how close they are to each other). 2. The reliability of an estimate (its repeatability) is reflected in the variation of estimates made by different methods of estimating or by different estimators.
Contributors to Estimates
10.20 | Financial Analysis | Purpose |  | is used to understand the financial aspects of an investment, a solution, or a solution approach.
|  | Description |  | Financial analysis is the assessment of the expected financial viability, stability, and benefit realization of an investment option.
|  | Elements | Cost of the Change | The cost of a change includes the expected cost of building or acquiring the solution components and the expected costs of transitioning the enterprise from the current state to the future state.
|  |  | Total Cost of Ownership (TCO) | is the cost to acquire a solution, the cost of using the solution, and the cost of supporting the solution for the foreseeable future, combined to help understand the potential value of a solution. | 有形的与无形的成本
|  |  | Value Realization | Value is typically realized over time.
|  |  | Cost-Benefit Analysis | is a prediction of the expected total benefits minus the expected total costs, resulting in an expected net benefit.
|  |  | Financial Calculations | Return on Investment: is expressed as a percentage measuring the net benefits divided by the cost of the change. Return on Investment = (Total Benefits – Cost of the Investment) / Cost of the Investment. The higher the ROI, the better the investment. | 1. 越高越好 2. 比较不同的ROI, 需要使用相同的时间周期
|  |  |  | Discount Rate: The discount rate is the assumed interest rate used in present value calculations. a larger discount rate is used for time periods that are more than a few years into the future to reflect greater uncertainty and risk. | 2. 越长约不好
|  |  |  | Present Value: To objectively compare the effects of these different rates and time periods, the benefits are calculated in terms of present-day value. Present Value = Sum of (Net Benefits in that period / (1 + Discount Rate for that period)) for all periods in the cost-benefit analysis. Present value is expressed in currency. The higher the present value, the greater the total benefit. Present value does not consider the cost of the original investment. | 1. 越高越好
|  |  |  | Net Present Value: is the present value of the benefits minus the original cost of the investment. Net Present Value = Present Value – Cost of Investment The higher the NPV, the better the investment. | 1. 越高越好
|  |  |  | Internal Rate of Return: is the interest rate at which an investment breaks even, and is usually used to determine if the change, solution or solution approach is worth investing in. Net Present Value = (-1 x Original Investment) + Sum of (net benefit for that period / (1 + IRR) for all periods) = 0. | 1. 越高越好
|  |  |  | Payback Period: The payback period provides a projection on the time period required to generate enough benefits to recover the cost of the change, irrespective of the discount rate. | 1. 越小越好
10.21 | Focus Groups | Purpose |  | A focus group is a means to elicit ideas and opinions about a specific product, service, or opportunity in an interactive group environment. The participants, guided by a moderator, share their impressions, preferences, and needs.
|  | Description |  | A focus group is composed of pre-qualified participants whose objective is to discuss and comment on a topic within a context. The participants share their perspectives and attitudes about a topic and discuss them in a group setting.
|  | Elements | Focus Group Objective
|  |  | Focus Group Plan | 1. Purpose 2. Location 3. Logistics 4. Participants 5. Budget 6. Timelines 7. Outcomes
|  |  | Participants | A successful focus group session has participants who are willing to both offer their insights and perspectives on a specific topic and listen to the opinions of the other participants.
|  |  | Discussion Guide | A discussion guide provides the moderator with a prepared script of specific questions and topics for discussion that meet the objective of the session.
Assign a Moderator and Recorder
Conduct the Focus Group
|  |  | After the Focus Group | The business analyst analyzes and documents the participants’ agreements and disagreements, looks for trends in the responses, and creates a report that summarizes the results.
10.22 | Functional Decomposition | Purpose |  | manage complexity and reduce uncertainty by breaking down processes, systems, functional areas, or deliverables into their simpler constituent parts and allowing each part to be analyzed independently.
|  | Description |  | Functional decomposition approaches the analysis of complex systems and concepts by considering them as a set of collaborating or related functions, effects, and components.
|  | Elements | Decomposition Objectives | 1. Measuring and Managing 2. Designing 3. Analyzing 4. Estimating and Forecasting 5. Reusing 6. Optimization 7. Substitution 8. Encapsulation
|  |  | Subjects of Decomposition | 1. Business Outcomes 2. Work to be Done 3. Business Process 4. Function 5. Business Unit 6. Solution Component 7. Activity 8. Products and Services 9. Decisions
Level of Decomposition
|  |  | Representation of Decomposition Results | 1. Tree diagrams 2. Nested diagrams 3. Use Case diagrams 4. Flow diagrams 5. State Transition diagrams 6. Cause-Effect diagrams 7. Decision Trees 8. Mind Maps 9. Component diagram 10. Decision Model and Notation
10.23 | Glossary | Purpose |  | defines key terms relevant to a business domain
|  | Description |  | Glossaries are used to provide a common understanding of terms that are used by stakeholders. A term may have different meanings for any two people. A list of terms and established definitions provides a common language that can be used to communicate and exchange ideas.
10.24 | Interface Analysis | Purpose |  | is used to identify where, what, why, when, how, and for whom information is exchanged between solution components or across solution boundaries.
|  | Description |  | An interface is a connection between two components or solutions.
|  | Elements | Preparing for Identification | The business analyst can leverage other techniques, such as document analysis, observation, scope modelling, and interviews, in order to understand which interfaces need to be identified.
|  |  | Conduct Interface Identification | Business analysts identify what interfaces are needed in the future state for each stakeholder or system that interacts with the system.
|  |  | Define Interfaces | Requirements for an interface are primarily focused on describing the inputs to and outputs from that interface, any validation rules that govern those inputs and outputs, and events that might trigger interactions. • the name of the interface, • the coverage or span of the interface, • the exchange method between the two entities, • the message format, and • the exchange frequency.
10.25 | Interviews | Purpose |  | is a systematic approach designed to elicit business analysis information from a person or group of people by talking to the interviewee(s), asking relevant questions, and documenting the responses.
|  | Description |  | The interview is a common technique for eliciting requirements. It involves direct communication with individuals or groups of people who are part of an initiative. 1. Structured Interview: in which the interviewer has a predefined set of questions. 2. Unstructured Interview: in which the interviewer does not have a predetermined format or order of questions. Questions may vary based on interviewee responses and interactions.
|  | Elements | Interview Goal
|  |  | Potential Interviewees |  | 潜在访谈者
Interview Questions
|  |  | Interview Logistics | 1. The location for the interview 2. Whether or not to record the interview, which may require the use of a scribe. 3. Whether or not to send the questions to the interviewees in advance 4. Whether the interview results will be confidential
Interview Flow
Interview Follow-Up
10.26 | Item Tracking | Purpose |  | is used to capture and assign responsibility for issues and stakeholder concerns that pose an impact to the solution.
|  | Description |  | Item tracking is an organized approach used by business analysts to address stakeholder concerns.
|  | Elements | Item Record | 1. Item Identifier 2. Summary 3. Category 4. Type 5. Date Identified 6. Identified By 7. Impact 8. Priority 9. Resolution Date 10. owner 11. Resolver 12. Agreed Strategy 13. Status 14. Resolution Updates 15. Escalation Matrix
|  |  | Item Management | Each item must be tracked to its closure or resolution.
Metrics
10.27 | Lessons Learned | Purpose |  | is to compile and document successes, opportunities for improvement, failures, and recommendations for improving the performance of future projects or project phases.
|  | Description |  | A lessons learned session (also known as a retrospective) helps identify either changes to business analysis processes and deliverables or successes that can be incorporated into future work
Elements
10.28 | Metrics and Key Performance Indicators (KPIs) | Purpose |  | measure the performance of solutions, solution components, and other matters of interest to stakeholders.
|  | Description |  | A metric is a quantifiable level of an indicator that an organization uses to measure progress.
|  | Elements | Indicators | An indicator displays the result of analyzing one or more specific measures for addressing a concern about a need, value, output, activity, or input in a table or graphical form. A good indicator has six characteristics: • Clear: precise and unambiguous. • Relevant: appropriate to the concern. • Economical: available at reasonable cost. • Adequate: provides a sufficient basis on which to assess performance. • Quantifiable: can be independently validated. • Trustworthy and Credible: based on evidence and research.
|  |  | Metrics | Metrics are quantifiable levels of indicators that are measured at a specified point in time.
|  |  | Structure | reliability, validity, and timeliness.
Reporting
10.29 | Mind Mapping | Purpose |  | is used to articulate and capture thoughts, ideas, and information.
|  | Description |  | Mind mapping is a form of note taking that captures thoughts, ideas, and information in a non-linear diagram. Business analysts use mind maps to: 1. think through and generate ideas on complex concepts or problems 2. explore relationships between the various facets of a problem in a way that inspires creative and critical thinking, and 3. present a consolidated view of complex concepts or problems
|  | Elements | Main Topic
Topics
Sub-topics
Branches
Keywords
Colour
Images
10.30 | Non-Functional Requirements Analysis | Purpose |  | Non-functional requirements analysis examines the requirements for a solution that define how well the functional requirements must perform. It specifies criteria that can be used to judge the operation of a system rather than specific behaviours (which are referred to as the functional requirements).
|  | Description |  | Non-functional requirements (also known as quality attributes or quality of service requirements) are often associated with system solutions, but they also apply more broadly to both process and people aspects of solutions.
|  | Elements | Categories of Non-Functional Requirements | 1. Availability 2. Compatibility 3. Functionality 4. Maintainability 5. Performance Efficiency 6. Portability 7. Reliability 可靠性 8. Scalability 9. Security 10. Usability 11. Certification 12. Compliance 合规性 13. Localization 14. Service Level Agreements 15. Extensibility 可扩展性
Measurement of Non-Functional Requirements
Context of Non-Functional Requirements
10.31 | Observation | Purpose |  | Observation is used to elicit information by viewing and understanding activities and their context
|  | Description |  | two basic approaches for observation: 1. Active/Noticeable 2. Passive/Unnoticeable
|  | Elements | Observation Objectives
Prepare for Observation
Conduct the Observation Session
Confirm and Present Observation Results
10.32 | Organizational Modelling | Purpose |  | Organizational modelling is used to describe the roles, responsibilities, and reporting structures that exist within an organization and to align those structures with the organization's goals.
|  | Description |  | An organizational model defines how an organization or organizational unit is structured.
|  | Elements | Types of Organizational Models | 1. Functionally-oriented: group staff together based on shared skills or areas of expertise and generally encourage a standardization of work or processes within the organization. 2. Market-oriented: may be intended to serve particular customer groups, geographical areas, projects, or processes rather than grouping employees by common skills or expertise. 3. The Matrix Model:
|  |  | Roles | Each role requires a certain set of skills and knowledge, has specific responsibilities, performs certain kinds of work, and has defined relationships with other roles in the organization.
|  |  | Interfaces | Interfaces (interactions) may be in the form of communication with people in other roles and work packages that the organizational unit receives from or delivers to other units.
|  |  | Organizational Charts | A box depicts: 1. Organizational Unit 2. Roles and People A line depicts: 1. Lines of Reporting
Influencers
10.33 | Prioritization | Purpose |  | Prioritization provides a framework for business analysts to facilitate stakeholder decisions and to understand the relative importance of business analysis information.
|  | Description |  | Prioritization is a process used to determine the relative importance of business analysis information. The importance may be based on value, risk, difficulty of implementation, or other criteria. These priorities are used to determine which business analysis information should be targeted for further analysis, which requirements should be implemented first, or how much time or detail should be allocated to the requirements. approaches: • Grouping: high, medium, low priority • Ranking: ordered from most to least important • Time boxing/Budgeting: based on allocation of a fixed resource (time or money) • Negotiation.
|  | Elements | Grouping | Grouping consists of classifying business analysis information according to predefined categories such as high, medium, or low priority.
|  |  | Ranking | Ranking consists of ordering business analysis information from most to least important.
|  |  | Time Boxing/Budgeting | Time boxing or budgeting prioritizes business analysis information based on the allocation of a fixed resource.
|  |  | Negotiation | The negotiation approach involves establishing a consensus among stakeholders as to which requirements will be prioritized.
10.34 | Process Analysis | Purpose |  | Process analysis assesses a process for its efficiency and effectiveness, as well as its ability to identify opportunities for change.
|  | Description |  | purpose: • recommending a more efficient or effective process, • determining the gaps between the current and future state of a process, • understanding factors to be included in a contract negotiation, • understanding how data and technology are used in a process, and • analyzing the impact of a pending change to a process. improve: • reducing the time required to complete a task or tasks in the process, • modifying interfaces or hand-offs between roles and organizational units to remove errors, including the reduction or elimination of bottlenecks, • automating steps that are more routine or predictable, and • increasing the degree of automation in the decision making required by the process. | 框架: Six Sigma and Lean 方法: value stream mapping, statistical analysis and control, process simulation, benchmarking, and process frameworks.
|  | Elements | Identify Gaps and Areas to Improve | Identifying gaps and areas to improve helps to identify what areas are in scope for analysis.
|  |  | Identify Root Cause | Identifying the root cause of the gaps and improvement areas ensures that the solution addresses the right gap and area.
|  |  | Generate and Evaluate Options | Generating options and alternative solutions to solve for the gap or area of improvement helps the team evaluate and see different points of view for improving the process.
|  |  | Common Methods | 1. SIPOC: Six Sigma 2. Value Stream Mapping (VSM): Lean
10.35 | Process Modelling | Purpose |  | Process modelling is a standardized graphical model used to show how work is carried out and is a foundation for process analysis.
|  | Description |  | Process models describe the sequential flow of work or activities. The most basic process model includes: a trigger event, a sequence of activities, and a result.
|  | Elements | Types of Process Models and Notations | 1. Flowcharts and Value Stream Mapping (VSM): used in the business domain. 2. Data Flow diagrams and Unified Modelling Language™ (UML®) diagrams: used in the information technology domain. 3. Business Process Model and Notation (BPMN): used across both business and information technology domains; is increasingly adopted as an industry standard. 4. Integrated DEFinition (IDEF) notation and Input, Guide, Output, Enabler (IGOE) diagrams: used for establishing scope. 5. SIPOC and Value Stream Analysis: used for process modelling.
|  |  | Flowchart | Flowcharts are used commonly with non-technical audiences and are good for gaining both alignment with what the process is and context for a solution. | A swimlane is a partitioned area (horizontal or vertical) that segregates those activities in the process that are carried out by a particular role.
|  |  | Business Process Model and Notation (BPMN) | Business Process Model and Notation (BPMN) provides an industry-standard language for modelling business processes in a form that is accessible by both business users and technical developers. | pool, A pool may include a number of swimlanes, each of which represents a role.
|  |  | Activity Diagram | The activity diagram is one of the use case realization diagrams defined in the Unified Modelling Language™ (UML®). | the activity diagram typically employs swimlanes to show responsibilities, synchronization bars to show parallel processing, and multiple exit decision points.
10.36 | Prototyping | Purpose |  | Prototyping is used to elicit and validate stakeholder needs through an iterative process that creates a model or design of requirements. It is also used to optimize user experience, to evaluate design options, and as a basis for development of the final business solution.
|  | Description |  | Prototyping is a proven method for product design.
|  | Elements | Prototyping Approach | 1. Throw-away 2. Evolutionary or Functional
|  |  | Prototyping Examples | 1. Proof of Principle or Proof of Concept 2. Form Study Prototype 3. Usability Prototype 4. Visual Prototype 5. Functional Prototype
|  |  | Prototyping Methods | 1. Storyboarding 2. Paper Prototyping 3. Workflow Modelling 4. Simulation
10.37 | Reviews | Purpose |  | Reviews are used to evaluate the content of a work product.
|  | Description |  | 1. Objectives: defining the purpose of the review. 2. Techniques: identifying either a formal or informal way to perform the review. 3. Participants: identifying who should take part in the review activity. Each review is focused on a work product, not the skills or actions of the participants.
|  | Elements | Objectives | • to remove defects, • to ensure conformance to specifications or standards, • to ensure the work product is complete and correct, • to establish consensus on an approach or solution, • to answer a question, resolve an issue, or explore alternatives, • to educate reviewers about the work product, and • to measure work product quality.
|  |  | Techniques | 1. Inspection 2. Formal Walkthrough (also known as Team Review) 3. Single Issue Review (also known as Technical Review) 4. Informal Walkthrough 5. Desk Check 6. Pass Around 7. Ad hoc
|  |  | Participants | 1. Author 2. Reviewer 3. Facilitator 4. Scribe
10.38 | Risk Analysis and Management | Purpose |  | Risk analysis and management identifies areas of uncertainty that could negatively affect value, analyzes and evaluates those uncertainties, and develops and manages ways of dealing with the risks.
|  | Description |  | Risk analysis and management involves identifying, analyzing, and evaluating risks. Where sufficient controls are not already in place, business analysts develop plans for avoiding, reducing, or modifying the risks, and when necessary, implementing these plans. Risk management is an ongoing activity. Continuous consultation and communication with stakeholders helps to both identify new risks and to monitor identified risks.
|  | Elements | Risk Identification | Risks are discovered and identified through a combination of expert judgment, stakeholder input, experimentation, past experiences, and historical analysis of similar initiatives and situations. The goal is to identify a comprehensive set of relevant risks and to minimize the unknowns. Risk identification is an ongoing activity.
|  |  | Analysis | Analysis of a risk involves understanding the risk, and estimating the level of a risk.
|  |  | Evaluation | The risk analysis results are compared with the potential value of the change or of the solution to determine if the level of risk is acceptable or not.
|  |  | Treatment | • Avoid: either the source of the risk is removed, or plans are adjusted to ensure that the risk does not occur. • Transfer: the liability for dealing with the risk is moved to, or shared with, a third party. • Mitigate: reduce the probability of the risk occurring or the possible negative consequences if the risk does occur. • Accept: decide not to do anything about the risk. If the risk does occur, a workaround will be developed at that time. • Increase: decide to take on more risk to pursue an opportunity.
10.39 | Roles and Permissions Matrix | Purpose |  | A roles and permissions matrix is used to ensure coverage of activities by denoting responsibility, to identify roles, to discover missing roles, and to communicate results of a planned change.
|  | Description |  | Role and permission allocation involves identifying roles, associating these with solution activities, and then denoting authorities who can perform these activities.
|  | Elements | Identifying Roles
Identifying Activities
|  |  | Identifying Authorities | Authorities are actions that identified roles are permitted to perform.
|  |  | Refinements | 1. Delegations 2. Inheritances
10.40 | Root Cause Analysis | Purpose |  | Root cause analysis is used to identify and evaluate the underlying causes of a problem.
|  | Description |  | Root cause analysis is a systematic examination of a problem or situation that focuses on the problem's origin as the proper point of correction rather than dealing only with its effects. used for: 1. Reactive Analysis 2. Proactive Analysis use four main activities: 1. Problem Statement Definition 2. Data Collection 3. Cause Identification 4. Action Identification
|  | Elements | The Fishbone Diagram
The Five Whys
10.41 | Scope Modelling | Purpose |  | Scope models define the nature of one or more limits or boundaries and place elements inside or outside those boundaries.
|  | Description |  | 1. In-scope 2. Out-of-scope 3. Both the basis for understanding the boundaries of: 1. Scope of Control 2. Scope of Need 3. Scope of Solution 4. Scope of Change
|  | Elements | Objectives
Scope of Change and Context
|  |  | Level of Detail | The purpose of analysis defines the appropriate level of abstraction at which scope elements are described.
|  |  | Relationships | 1. Parent-Child or Composition-Subset 2. Function-Responsibility 3. Supplier-Consumer 4. Cause-Effect 5. Emergent
Assumptions
Scope Modelling Results
10.42 | Sequence Diagrams | Purpose |  | Sequence diagrams are used to model the logic of usage scenarios by showing the information passed between objects in the system through the execution of the scenario.
|  | Description |  | A sequence diagram shows how processes or objects interact during a scenario. The classes required to execute the scenario and the messages they pass to one another (triggered by steps in the use case) are displayed on the diagram. Sequence diagrams are sometimes called event diagrams. | UML
|  | Elements | Lifeline | A lifeline represents the lifespan of an object during the scenario being modelled in a sequence diagram.
|  |  | Activation Box | An activation box represents the period during which an operation is executed.
|  |  | Message | A message is an interaction between two objects. • Synchronous Call: transfers control to the receiving object. The sender cannot act until a return message is received. • Asynchronous Call: (also known as a signal) allows the object to continue with its own processing after sending the signal. The object may send many signals simultaneously, but may only accept one signal at a time.
10.43 | Stakeholder List, Map, or Personas | Purpose |  | Stakeholder lists, maps, and personas assist the business analyst in analyzing stakeholders and their characteristics. This analysis is important in ensuring that the business analyst identifies all possible sources of requirements and that the stakeholder is fully understood so decisions made regarding stakeholder engagement, collaboration, and communication are the best choices for the stakeholder and for the success of the initiative.
|  | Description |  | Stakeholder analysis involves identifying the stakeholders that may be affected by a proposed initiative or that share a common business need. Stakeholder analysis notes, considers, and analyzes the various characteristics of the identified stakeholders.
|  | Elements | Stakeholder Lists
|  |  | Stakeholder Map | Stakeholder maps are diagrams that depict the relationship of stakeholders to the solution and to one another. 1. Stakeholder Matrix 2. Onion Diagram
Responsibility (RACI) Matrix
Personas
10.44 | State Modelling | Purpose |  | State modelling is used to describe and analyze the different possible states of an entity within a system, how that entity changes from one state to another, and what can happen to the entity when it is in each state.
|  | Description |  | An entity is an object or concept within a system. An entity may be used in several processes. The life cycle of every entity has a beginning and an end. • a set of possible states for an entity, • the sequence of states that the entity can be in, • how an entity changes from one state to another, • the events and conditions that cause the entity to change states, and • the actions that can or must be performed by the entity in each state as it moves through its life cycle.
|  | Elements | State | An entity has a finite number of states during its life cycle, although it can be in more than one state at a time.
State Transition
State Diagram
State Tables
10.45 | Survey or Questionnaire | Purpose |  | A survey or questionnaire is used to elicit business analysis information—including information about customers, products, work practices, and attitudes—from a group of people in a structured way and in a relatively short period of time.
|  | Description |  | Close-ended: the respondent is asked to select from a list of predefined responses, such as a Yes/No response, a multiple-choice selection, a rank/order decision, or a statement requiring a level of agreement. Open-ended: the respondent is asked to answer questions in a free form without having to select an answer from a list of predefined responses.
|  | Elements | Prepare | 1. Define the objective 2. Define the target survey group 3. Choose the appropriate survey or questionnaire type 4. Select the sample group 5. Select the distribution and collection methods 6. Set the target level and timeline for response: If the actual response rate is lower than the acceptable threshold, the use of the survey results may be limited. 7. Determine if the survey or questionnaire should be supported with individual interviews 8. Write the survey questions 9. Test the survey or questionnaire
Distribute the Survey or Questionnaire
|  |  | Document the Results | • collate the responses, • summarize the results, • evaluate the details and identify any emerging themes • formulate categories for encoding the data, and • break down the data into measurable increments.
10.46 | SWOT Analysis | Purpose |  | SWOT analysis is a simple yet effective tool used to evaluate an organization's strengths, weaknesses, opportunities, and threats to both internal and external conditions.
|  | Description |  | SWOT analysis is used to identify the overall state of an organization both internally and externally.
|  | Elements | Strengths (S) | anything that the assessed group does well.
|  |  | Weaknesses (W) | actions or functions that the assessed group does poorly or not at all.
|  |  | Opportunities (O) | external factors of which the assessed group may be able to take advantage.
|  |  | Threats (T) | external factors that can negatively affect the assessed group
10.47 | Use Cases and Scenarios | Purpose |  | Use cases and scenarios describe how a person or system interacts with the solution being modelled to achieve a goal.
Description
|  | Elements | Use Case Diagram | A use case diagram visually depicts the scope of the solution, by showing the actors who interact with the solution, which use cases they interact with, and any relationships between the use cases.
|  |  | Use Case Description | 1. Name 2. Goal 3. Actors 4. Preconditions 5. Trigger 6. Flow of Events 7. Post-conditions or Guarantees
10.48 |  | Purpose |  | A user story represents a small, concise statement of functionality or quality needed to deliver value to a specific stakeholder.
|  | Description |  | User stories capture the needs of a specific stakeholder and enable teams to define features of value to a stakeholder using short, simple documentation. • to capture stakeholder needs and prioritize development of solutions, • as a basis of estimating and planning solution delivery, • as a basis for generating user acceptance tests, • as a metric for measuring the delivery of value, • as a unit for tracing related requirements, • as a basis for additional analysis, and • as a unit of project management and reporting.
|  | Elements | Title (optional)
|  |  | Statement of Value | • Who: a user role or persona. • What: a necessary action, behaviour, feature, or quality. • Why: the benefit or value received by the user when the story is implemented.
|  |  | Conversation | User stories help teams to explore and understand the feature described in the story and the value it will deliver to the stakeholder.
|  |  | Acceptance Criteria | A user story may be supported through the development of detailed acceptance criteria
10.49 | Vendor Assessment | Purpose |  | A vendor assessment assesses the ability of a vendor to meet commitments regarding the delivery and the consistent provision of a product or service.
Description
|  | Elements | Knowledge and Expertise | A common reason for using third-party vendors is that they can provide knowledge and expertise not available within the organization.
|  |  | Licensing and Pricing Models | The licensing or pricing model is taken into account in cases where a solution or solution component is purchased from or outsourced to a third party vendor.
Vendor Market Position
Terms and Conditions
Vendor Experience, Reputation, and Stability
10.50 | Workshops | Purpose |  | Workshops bring stakeholders together in order to collaborate on achieving a predefined goal.
|  | Description |  | A workshop is a focused event attended by key stakeholders and subject matter experts (SMEs) for a concentrated period of time. Workshops generally include: • a representative group of stakeholders, • a defined goal, • interactive and collaborative work, • a defined work product, and • a facilitator.
|  | Elements | Prepare for the Workshop
|  |  | Workshop Roles | 1. Sponsor 2. Facilitator 3. Scribe 4. Timekeeper 5. Participants
Conduct the Workshop
|  |  | Post Workshop Wrap-up | After the workshop, the facilitator follows up on any open action items that were recorded at the workshop, completes the documentation, and distributes it to the workshop attendees and any stakeholders who need to be kept informed of the work done.
Note on B2: chloroplast: 验收和评估标准
Note on D40: chloroplast: 评估备选方案
Note on B42: chloroplast: 商业模式画布
Note on E43: chloroplast: Customer Segments: 客户群体
Note on D47: chloroplast: 价值主张
Note on E48: chloroplast: 客户获取和客户保留
Note on D50: chloroplast: 客户群
Note on D52: chloroplast: 收入流
Note on E62: chloroplast: Affinity Map: 亲和图
Note on E110: chloroplast: forecast: 预测，预报
Note on E112: chloroplast: Parametric: 参数 calibrated: 校准 Rough Order of Magnitude (ROM): 估算 extrapolated: 推测
Note on E114: chloroplast: Analogous: 类似
Note on E115: chloroplast: Precision: 精度
Note on E120: chloroplast: foreseeable: 可预知的，可预料的
Note on E127: chloroplast: breaks even: 平衡，不赚不赔
Note on E130: chloroplast: moderator: 主持人
Note on E132: chloroplast: Logistics: 后勤
Note on B144: chloroplast: 术语表
Note on E156: chloroplast: scribe: 抄写员 confidential: 保密的
Note on D158: chloroplast: 访谈的后续工作
Note on E159: chloroplast: pose: 造成，引起
Note on E165: chloroplast: incorporated: 合并的
Note on E170: chloroplast: Adequate: 适当的 Quantifiable: 可计量的
Note on E174: chloroplast: articulate: 明确表达
Note on E175: chloroplast: consolidated: 统一的
Note on D199: chloroplast: 组织图
Note on E221: chloroplast: Evolutionary 进化
Note on E227: chloroplast: Ad hoc: 特别, 临时
Note on E234: chloroplast: pursue: 追求
Note on E240: chloroplast: Delegations: 委托
Note on E242: chloroplast: Reactive: 对比 Proactive: 主动
Note on D243: chloroplast: 鱼骨图
Note on D244: chloroplast: 五问法
Note on D263: chloroplast: 人物画像
Note on E285: chloroplast: concise: 简明的
Note on E291: chloroplast: consistent: 提供

## chapter11
章节 | 分类 | 标题 | 概念 | 理解
The Agile Perspective
| 11.1.1 | Change Scope | Breadth of Change
Depth of Change
|  |  | Value and Solutions Delivered | agile approach is the emphasis on delivering value early in a highly collaborative manner, using adaptive planning that has a focus on continuous improvement.
|  |  | Delivery Approach | Agile approaches focus on people interactions, transparent communications, and ongoing delivery of valuable change to stakeholders.
Major Assumptions
| 11.1.2 | Business Analysis Scope | Change Sponsor
Change Targets and Agents
Business Analyst Position
Business Analysis Outcomes
| 11.1.3 | Approaches and Techniques | Approaches | 1. Crystal Clear 2. Disciplined Agile Delivery (DAD) 3. Dynamic Systems Development Method (DSDM) 4. Evolutionary Project Management (Evo) 5. Extreme Programming (XP) 6. Feature Driven Development (FDD) 7. Kanban 8. Scaled Agile Framework®(SAFe™) 9. Scrum
|  |  | Techniques | Behaviour Driven Development (BDD) | An approach that enhances the communication between stakeholders and team members by expressing product needs as concrete examples.
|  |  |  | Kano Analysis | A technique for understanding which product features will help drive customer satisfaction.
|  |  |  | Lightweight Documentation | A principle that governs all documentation produced on an agile project. The purpose is to ensure that all documentation is intended to fulfill an impending need, has clear value for stakeholders, and does not create unnecessary overhead. For example, a system overview document may be written towards the end of a project based on stable content and acceptance tests written as part of the product testing.
|  |  |  | MoSCoW Prioritization | A method to prioritize stories (or other elements) in incremental and iterative approaches. MoSCoW (must have, should have, could have, won’t have) provides a way to reach a common understanding on relative importance of delivering a story or other piece of value in the product.
|  |  |  | Personas | Fictional characters or archetypes that exemplify the way that typical users interact with a product.
|  |  |  | Planning Workshop | A collaborative workshop that is used to allow an agile team to determine what value can be delivered over a time period such as a release.
|  |  |  | Purpose Alignment Model | A model that is used to assess ideas in the context of customer and value.
|  |  |  | Relative Estimation | Team estimation techniques using either story points, which represent the relative complexity of a user story to develop, or ideal days, which represent the amount of total effort a story would take to develop.
|  |  |  | Retrospectives | A similar term for the Lesson Learned technique. Retrospectives focus on continuous improvement of the teamwork process and are held after every iteration on agile projects.
|  |  |  | Story Decomposition | Ensures that the requirements for a product are represented at the appropriate level of detail and are derived from a valuable business objective.
|  |  |  | Story Mapping | Provides a visual and physical view of the sequence of activities to be supported by a solution.
|  |  |  | Storyboarding | Detail visually and textually the sequence of activities that represent user interactions with a system or business.
|  |  |  | Value Stream Mapping | Provides a complete, fact-based, time-series representation of the stream of activities required to deliver a product or service to the customer.
| 11.1.4 | Underlying Competencies | Communication and collaboration
Patience and tolerance
Flexibility and adaptability
Ability to handle change
Ability to recognize business value
Continuous improvement
| 11.1.5 | Impact on Knowledge Areas | Business Analysis Planning and Monitoring | In agile approaches, detailed business analysis planning can be deferred until work on an activity is ready to begin rather than done upfront as in predictive projects.
|  |  | Elicitation and Collaboration | Progressive elicitation and elaboration occur throughout an agile initiative.
|  |  | Requirements Life Cycle Management | As agile initiatives unfold, the scope is defined with increasing specificity
|  |  | Strategy Analysis | Strategy analysis is a constant part of an agile initiative to ensure that the solution delivered continues to provide value to stakeholders.
|  |  | Requirements Analysis and Design Definition | Needs are progressively elaborated during an agile project.
|  |  | Solution Evaluation | the stakeholders and agile team continually assess and evaluate the development solution as it is incrementally built and refined. Evaluation of the evolving solution with the stakeholders occurs at the end of every development cycle to ensure the deliverable meets their needs and satisfies their expectations. The business analyst ensures that the product meets expectations before a product is released, and identifies new opportunities that will add value to the business.
The Business Intelligence Perspective | 11.2.1 | Change Scope | Breadth of Change
Depth of Change
Value and Solutions Delivered
Delivery Approach
Major Assumptions
| 11.2.2 | Business Analysis Scope | Change Sponsor
Change Targets
Business Analyst Position
|  |  | Business Analysis Outcomes | 1. Business process coverage 2. Decision models 3. Source logical data model and data dictionary 4. Source data quality assessment 5. Target logical data model and data dictionary 6. Transformation rules 7. Business analytics requirements 8. Solution architecture
| 11.2.3 | Methodologies and Approaches | Types of Analytics | Descriptive analytics | uses historical data to understand and analyze past business performance.
|  |  |  | Predictive analytics | applies statistical analysis methods to historical data to identify patterns, and then uses that understanding of relationships and trends to make predictions about future events.
|  |  |  | Prescriptive analytics | expands on predictive analytics to identify decisions to be made and to initiate appropriate action to improve business performance.
|  |  | Supply and Demand Driven | Supply-driven | This approach maps existing systems data to define what data is available
|  |  |  | Demand-driven | This approach starts with identifying the information output needed to support business decisions, and then tracing that information back to the underlying data sources to determine feasibility and cost.
|  |  | Structured and Unstructured Data | Structured data
Unstructured data
| 11.2.4 | Underlying Competencies
| 11.2.5 | Impact on Knowledge Areas
The Information Technology Perspective
| 11.3.1 | Change Scope | Create a new organizational capability
Achieve an organizational objective by enhancing an existing capability
Facilitate an operational improvement
Maintain an existing information technology system
Repair a broken information technology system
The Business Architecture Perspective
| 11.4.3 | Reference Models and Techniques | Reference Models | Association for Cooperative Operations Research and Development (ACORD) | Insurance and Financial industries
|  |  |  | Business Motivation Model (BMM) | Generic
|  |  |  | Control Objectives for IT (COBIT) | IT governance and management
|  |  |  | eTOM and FRAMEWORX | Communications sector
|  |  |  | Federal Enterprise Architecture Service Reference Model (FEASRM) | Government (developed for the U.S. Federal Government)
|  |  |  | Information Technology Infrastructure Library (ITIL®) | IT service management
|  |  |  | Process Classification Framework (PCF) | Multiple sectors including aerospace, defence, automotive, education, electric utilities, petroleum, pharmaceutical, and telecommunications
|  |  |  | Supply Chain Operations Reference (SCOR) | Supply chain management
|  |  |  | Value Reference Model (VRM) | Value change and network management
|  |  | Techniques | Archimate | An open standard modelling language.
|  |  |  | Business Motivation Model (BMM) | A formalization of the business motivation in terms of mission, vision, strategies, tactics, goals, objectives, policies, rules, and influencers.
|  |  |  | Business Process Architecture | The modelling of the processes, including interface points, as a means of providing a holistic view of the processes that exist within an organization.
|  |  |  | Capability Map | A hierarchical catalogue of business capabilities, or what the business does. Capabilities are categorized according to strategic, core, and supporting.
|  |  |  | Customer Journey Map | A model that depicts the journey of a customer through various touch points and the various stakeholders within the service or organization. Customer journey maps are frequently used to analyze or design the user experience from multiple perspectives.
|  |  |  | Enterprise Core Diagram | Models the integration and standardizations of the organization.
|  |  |  | Information Map | A catalogue of the important business concepts (fundamental business entities) associated with the business capabilities and value delivery. This is typically developed in conjunction with the capability model and represents the common business vocabulary for the enterprise. It is not a data model but rather a taxonomy of the business.
|  |  |  | Organizational Map | A model that shows the relationship of business units to each other, to external partners, and to capabilities and information. Unlike a typical organizational chart the map is focused on the interaction between units, not the structural hierarchy.
|  |  |  | Project Portfolio Analysis | Used to model programs, projects, and portfolios to provide a holistic view of the initiatives of the organization.
|  |  |  | Roadmap | Models the actions, dependencies, and responsibilities required for the organization to move from current state, through the transition states, to the future state.
|  |  |  | Service-Oriented Analysis | Used to model analysis, design, and architecture of systems and software to provide a holistic view of the IT infrastructure of the organization.
|  |  |  | The Open Group Architecture Framework (TOGAF®) | Provides a method for developing enterprise architecture. Phase B of the TOGAF Architecture Development Method (ADM) is focused on the development of business architecture. Organizations following TOGAF may choose to tailor Phase B to adopt the business architecture blueprints, techniques, and references described in the BABOK® Guide.
|  |  |  | Value Mapping | Value mapping provides a holistic representation of the stream of activities required to deliver value. It is used to identify areas of potential improvement in an end–to–end process. Although there are several different types of value mapping, a value stream is often used in business architecture.
|  |  |  | Zachman Framework | Provides an ontology of enterprise primitive concepts based on a matrix of six interrogatives (what, how, where, who, when, why) and six levels of abstraction (executive, business management, architect, engineer, technician, enterprise). Business architects may find that exploring the executive or business management perspectives across the different interrogatives provides clarity and insight.
The Business Process Management Perspective
|  | Frameworks, Methodologies, and Techniques | Frameworks | ACCORD | A methodological framework that maps current state models, as well as unstructured data, to conceptual models.
|  |  |  | Enhanced Telecommunications Operations Map (eTOM) | A hierarchical framework developed for the telecommunications industry that has been adopted by other service-oriented industries.
|  |  |  | Governments Strategic Reference Model (GSRM) | A life cycle framework that provides generic government processes and patterns for each stage of organizational maturity.
|  |  |  | Model based and Integrated Process Improvement (MIPI) | A cyclical framework whose steps include assess readiness, outline process under review, detail data collection, form model of current process, assess and redesign process, implement improved process, and review process.
|  |  |  | Process Classification Framework(PCF) | A classification framework that details processes and is used for benchmarking and performance measurement.
|  |  | Methodologies | Adaptive Case Management (ACM) | A method used when processes are not fixed or static in nature, and have a lot of human interaction. An ACM process may be different each time it is performed.
|  |  |  | Business Process Reengineering (BPR) | The fundamental rethinking and redesigning of business processes to generate improvements in critical performance measures, such as cost, quality, service, and speed.
|  |  |  | Continuous Improvement (CI) | The ongoing monitoring and adjustment of existing processes to bring them closer to goals or performance targets. This represents a permanent commitment of the organization to change and must be an important part of its culture.
|  |  |  | Lean | A continuous improvement methodology that focuses on the elimination of waste in a process, defined as work for which the customer of the process will not pay.
|  |  |  | Six Sigma | A continuous improvement methodology that focuses on the elimination of variations in the outcome of a process. It is statistically oriented and performance data centric.
|  |  |  | Theory Of Constraints (TOC) | A methodology that holds the performance of an organization can be optimized by managing three variables: the throughput of a process, operational expense to produce that throughput, and the inventory of products. The performance of a process is dominated by one key constraint at any given time, and the process can only be optimized by improving the performance of that constraint.
|  |  |  | Total Quality Management (TQM) | A management philosophy that holds to the underlying principle that the processes of the organization should provide the customer and stakeholders, both internal and external, with the highest quality products and services, and that these products or services meet or exceed the customers' and stakeholders' expectations.
|  |  | Techniques | Cost Analysis | A list of the cost per activity totaled to show the detailed cost of the process and is used frequently by businesses to gain an understanding and appreciation of the cost associated with a product or service. Cost analysis is also known as activity based costing.
|  |  |  | Critical to Quality (CTQ) | A set of diagrams, in the form of trees, that assist in aligning process improvement efforts to customer requirements. CTQ is a technique used in Six Sigma, but is not exclusive to Six Sigma
|  |  |  | Cycle-time Analysis | An analysis of the time each activity takes within the process. Cycle-time analysis is also known as a duration analysis.
|  |  |  | Define Measure Analyze Design Verify (DMADV ) | A data-driven structured roadmap used to develop new or improve existing processes. DMADV is a technique used in Six Sigma, but is not exclusive to Six Sigma.
|  |  |  | Define Measure Analyze Improve Control (DMAIC) | A data-driven structured roadmap used to improve processes. DMAIC is a technique used in Six Sigma, but is not exclusive to Six Sigma.
|  |  |  | Drum-Buffer-Rope (DBR) | A method used to ensure that the system constraint always functions at the maximum possible output, by ensuring that there is a sufficient buffer of materials just prior to the constraint to keep it continuously busy. It can be used in BPM to ensure process efficiency.
|  |  |  | Failure Mode and Effect Analysis (FMEA) | A systematic method of investigating process failures and defects, and identifying potential causes. FMEA is a technique that assists in locating problems in the as-is process and correcting them when developing the to-be processes.
|  |  |  | House of Quality/Voice of Customer | A matrix relating customer desires and product characteristics to the capabilities of an organization. It is a technique that could be used in developing the to-be processes.
|  |  |  | Inputs, Guide, Outputs, Enablers (IGOE) | A diagram that describes the context of a process, by listing the inputs and outputs of the process, the guides that are used to inform the execution of the process, and the supporting tools and information required for the process.
|  |  |  | Kaizen Event | A focused, rapid effort to improve value delivery in one specific activity or sub-process.
|  |  |  | Process Simulation | A model of the process and a set of randomized variables to allow for multiple variations of a process to be assessed and develop an estimate of their performance under actual conditions.
|  |  |  | Suppliers Inputs Process Outputs Customers (SIPOC) | A table that summarizes inputs and outputs from multiple processes. Also known as COPIS, which is simply SIPOC spelled backwards.
|  |  |  | Theory of Constraints (TOC) Thinking Processes | A set of logical cause-and-effect models used to diagnose conflicts, identify the root causes of problems, and define future states of a system that successfully resolve those root causes. TOC thinking processes is a technique that assists in locating problems in the as-is process and correcting them when developing the to-be processes.
|  |  |  | Value Added Analysis | Looks at the benefit to the customer added at each step of a process to identify opportunities for improvement.
|  |  |  | Value Stream Analysis | Used to assess the value added by each functional area of a business to the customer, as part of an end-to-end process.
|  |  |  | Who What When Where Why (5Ws) | A set of questions that form the foundation for basic information gathering. The 5Ws may also include How added to become the 5Ws and a H.
Note on D9: chloroplast: Agents: 媒介
Note on F33: chloroplast: Progressive: 渐进的
Note on F34: chloroplast: 随着敏捷计划的展开，范围的定义越来越具体。
Note on F36: chloroplast: progressively elaborated：逐步细化
Note on F47: chloroplast: 描述性分析
Note on F49: chloroplast: Prescriptive: 规范